## Slide 1: MESA project status
MAGIX workshop February, 17 2017
Kurt Aulenbacher
for the MESA project team

## Slide 2: Outline
Building Overview and Accelerator Layout
Cryomodule Production Status
MAGIX beam dynamics issues
Timelines : components, building, installation, comissioning

## Slide 3
MESA Building Overview
Picture: D. Simon
Extension of the halls provides great advantages to experiments and accelerator layout
Additional space for future experiments availiable
Possibility to run BDX Trade off: Project delay ~3 years due to civil construction time, accelerator layout needed to be adapted to the new situation

## Slide 4
MESA Accelerator Layout
Double sided recirculation design with normalconducting injector and superconducting main linac
Two different modes of operation: - EB-operation (P2/BDX experiment): polarized beam, up to 150 µA @ 155 MeV - ERL-operation (MAGIX experiment): (un)polarized beam, up to 1 (10) mA @ 105 MeV
Picture: D. Simon
Gun
MELBA
MAMBO
MEEK-1
MEEK-2
Recirculation arcs 1-3-5
Recirculation arcs 2-4
Ext. beamline
ERL loop
155 MeV dump
5 MeV dump
P2
MAGIX

## Slide 5: MESA Cryomodules
Picture: HZDR
Cryomodules are the backbone of the new accelerator
We ordered Cryomodules of the 'Rossendorf'-type (2 x 9-cell TESLA/XFEL cavities), which are in use at ELBE will be used for MESA
→ we applied some adaptations in order to allow 1 mA ERL operation:
(PhD thesis T. Stengler)
added tuners with piezo elements (XFEL/Saclay-type)
used sapphire windows at HOM feedthroughs + many smaller
improvements
→ maximum beam current with reasonable
effort currently being investigated
in Accelence-PhD project (Christian Stoll), realization is PRISMA+ project.

## Slide 6: Cryomodule Project Status
Project duration until today: 20 months
Cavities and couplers are completed
Cavity next step: Helium tank welding and cold acceptance tests at DESY (March)
Couplers next step: rf power-conditioning at HZDR ( March)
Cryostat Vessels have been completed (January 2017).
4K/2K distribution box developed together with DESY (Final design review 15/Feb)
After succesful tests (?)cavity string assembly can start in the clean room at RI
(earliest: April/May)
Delivery of the first module planned End June 2017 second in August
Testing still possible at HIM until
spring 2018

## Slide 7
Summer 2016 „Helmholtz Institut Mainz“ (HIM) is now ready for operation
(Installations for Cryomodukes need considerable effort!)!
He: Lq. Helium supply line from liquifier in nuclear physics institute: >50l/hour through 220 m
long pipe demonstrated. P: 4g/s pump stage at 16mbar has been ordered.
I: Instrumentation platform, 15kW semiconductor amplifier has been ordered, delivery 4/2017
C: Clean room for cryomodule maintenance. B=Bunker (installed by now…)
Test bunker for SRF cryomodules
He
P
Experimental Hall
C
I
01 June 2016
B
Cryomodules-preparing for the test phase

## Slide 8: BEAM DYNAMICS FOR MESA/MAGIX Energy spread in recirculating electron linacs
Work by Florian Hug, R. Heine , D. Simon

## Slide 9: Outline
  Motivation
  Acceleration in isochronous vs. non-isochronous recirculators
  MESA
  External beam operation
  ERL operation
MAMBO stability: influence on MESA operation
Summary and Outlook

## Slide 10: Motivation
Goal: Provide excellent and stable beam for experiments
e.g. line-width in electron scattering experiments:
 Different error contributions sum up statistically independent
Typical values:
DET/ET ≈ 1.5 ∙ 10-4 DESp/ESp ≈ 1-3 ∙ 10-4
Requirements on electron beam (not being the major contribution):
DErms/E < 1 ∙ 10-4 (+excellent long term beam stability )

## Slide 11: Acceleration in electron linacs
For relativistic electrons (v≈c): almost no changes in longitudinal position within bunch
Acceleration on crest of the rf-wave:
Short bunches needed because bunchlength causes energy spread!
Particles stay “frozen” at their longitudinal position within the bunch

## Slide 12: Isochronous recirculation scheme
Convenient for long linacs with many cavities:
Acceleration on crest of rf field with shortest possible bunches
 Errors scale with (N = number of cavities)
injector
recirculations
extraction
LINAC
isochron (r56=0)‏
no long. dispersion (r56=0)
S= 0
In (short) few turn recirculators:
Amplitude errors of accelerating cavities can add up coherently over all turns  no averaging of errors when tlinac << tcavity
 Energy spread can exceed experimental requirements
no long. dispersion (r56=0)

## Slide 13: Non-isochronous recirculation scheme
Common operation mode for microtrons and synchrotrons
Acceleration on edge of rf field
Different time of flight for particles having different energies
injector
recirculations
extraction
LINAC
long. dispersion (r56)
S ≠ 0
long. dispersion (r56)
Particles perform synchrotron oscillations in longitudinal phase space
Half- or full integer oscillations lead to reproduction of the longitudinal phase space at injection [Herminghaus, NIM A 305 (1991) 1].
 complete compensation of rf phase- and amplitude jitters possible

## Slide 14: MESA: External Beam Operation
Simulations for a new longitudinal working point
Goal: Find optimal combination of r56 and
FS for MESA 6-pass external beam mode
Import longitudinal phase space from MAMBO 150 µA simulation
Create randomized cavity parameters (4 cavities, DArms= 1 ∙ 10-4, Dfrms= 0.1°)
For each pair of r56 and FS track each particle through the accelerator
Calculate rms energy spread for each pair of r56 and FS
Chart: 
Phase [deg]
Energy [MeV]

## Slide 15: MESA: External Beam Operation
Results for 6-pass external beam mode:
best energy spread at:
r56 = -2.6 mm/% and
FS = -5.8°
DErms/E = 5.5 ∙ 10-5
isochronous: DErms/E = 3.4 ∙ 10-4

## Slide 16: MESA: ERL Operation
isochronous operation
Accelerating and decelerating bunches in phase with maximum/minimum of rf-field
Decelerating bunches re-enter cavities at a different phase  possible disturbance on accelerating phase as well
Compare the two different ERL operation modes:
non-isochronous operation
On the non-isochronous working efficiency of energy recovery decreases
Maybe challenging for rf-control system to sustain desired accelerating field
Chart: 

## Slide 17: MESA: ERL Operation
Simulations for isochronous ERL operation
Only 4 passes in ERL mode
High space charge forces at maximum
beam current
Import longitudinal phase space from MAMBO 1 mA simulation
Create randomized cavity parameters (4 cavities, DArms= 1 ∙ 10-4, Dfrms= 0.1°)
Track each particle through the accelerator
Calculate rms energy spread and longitudinal phase space
Phase [deg]
Energy [MeV]
Chart: 

## Slide 18: MESA: ERL Operation
Results for 4-pass isochronous ERL mode:
Phase space dominated
by cosine shape of
accelerating field
DErms/E = 7.16 ∙ 10-4
 75 keV @ 105 MeV
Phase [deg]
Energy error [MeV]

## Slide 19: MAMBO : ERL Operation
Injector properties affecting 4-pass isochronous ERL mode:
shorter bunches at higher energy spread can improve energy spread at experiment
MAMBO is optimized for best energy spread so far

## Slide 20: MESA: non-iso ERL Operation
Maybe a different non-isochronous scheme in ERL operation possible?
Use the double sided design of MESA
First two passes acceleration on edge
Use r56 for a half turn in phase space
Second two passes acceleration on opposite edge
Use r56 for a half turn in phase space (other direction)
end up with better energy spread
Deceleration vice-versa
further optimization maybe possible by better matching to injector beam
DErms/E = 2.68 ∙ 10-4 (28.8 keV @ 105 MeV)

## Slide 21: MESA: Energy variation 50-100 MeV
DErms/E = 2.68 ∙ 10-4 (28.8 keV @ 105 MeV)
Going down from 10550 Zero order:
- Varying iMAMBO probably very tedious and detrimental since Imax~pin
-Achieve 50 MeV+x by reducing energy gain per turn
(27,5, 50MeV)
- First order: But defelction angles scale liek energies 105/55=1,0909
is not equal 50/27,5 =1,81

## Slide 22
MESA Energy variation
Going down from 10575 MeV Zero order:
- Varying MAMBO energy probably very tedious and detrimental since Imax~pin
-Achieve 75 MeV+x by reducing energy gain per turn
(35+5, 70+5 MeV)
- First order: But defelction angles scale liek energies 105/55=1,0909
is not equal 75/40 =1,875  can probably be corrected , since more space
available inspreaders

## Slide 23: MESA: timelines
DErms/E = 2.68 ∙ 10-4 (28.8 keV @ 105 MeV)
Kryomodules: delivery summer 17
 Tested and in store summer 2018?
Kryoplant: Modifikations & purchase SAC& transfer lines (?)
‚in 2018/19
MAMBO: (structures& transmitters) Order not before end 2017 , delivery until mid 2019,
Tested and in store beginning 2020 ?
Magnets: Order summer 2017, delivery end 2018
Vacuum, controls, etc...also feasible before 2020 (money?)
BUILDING: so far on time, finalization foreseen October 2020.
Earlier access, depends on LBB and architects.
2019-2020: Intense planning, resource allocation required  No realistic
installation/commisioning schedule so far.

## Slide 24: MESA: timelines
DErms/E = 2.68 ∙ 10-4 (28.8 keV @ 105 MeV)

## Slide 25: Summary & Outlook
a non-isochronous working point can improve the energy spread and the stability of a recirculated beam significantly, even when only few turns of recirculation are used
a proper energy spread and a phase stabilization of the injector beam is important. Short bunchlength after injector seems to be more important than heading for best energy spread
at MESA a non-isochronous recirculation scheme is planned for the external beam mode but further simulations still have to be done to find the optimum set of parameters
for ERL mode at MESA further investigations are needed in order to figure out the possibility of such a system

## Slide 26: Thank you for your attention!

## Slide 27: Supplement slides

## Slide 28: MAMBO stability
In MAMBO rf jitters can have effects on:
Bunchlength
Extraction phase
Energy spread
Mean energy Here: calculations for 150 µA by Robert Heine
 Investigate how EB and ERL mode are affected

## Slide 29: MAMBO : ERL Operation
Injector properties affecting 4-pass isochronous ERL mode:
shorter bunches at higher energy spread can improve energy spread at experiment
MAMBO is optimized for best energy spread so far

## Slide 30: MAMBO: EB operation
Injector properties affecting 6-pass non-isochronous ERL mode:
In EB operation energy spread stays well below 10-4
Mean energy can vary with respect to MAMBO properties
Numbers need to be cross- checked with P2 demands

## Slide 31: MESA: non-iso ERL Operation
Phase [deg]
Energy error [MeV]

## Slide 32
MAMI and MESA at KPH Mainz
MAMI is operating since >25 years at KPH
In 2012 funding of PRISMA cluster of excellence has been granted including a new accelerator project: Mainz Energy Recovery Superconducting Accelerator (MESA) to be built in the exisisting facility
In June 2015 DFG granted a research building to JGU „Center for Fundamental Physics (CFP)“ including an extension for MESA halls

## Slide 33: MESA Injector Test Setup
Picture: S. Friederich

## Slide 34
Other subsystems until 2020– careful optimization of the more „conventional“ systems !
- r.f. system : Semiconductor amplifiers (of strategic importance but expensive!)
Cryoplant (discussion with vendor for extension completed, order in ~2018)
Recirculations arcs and experimental beamlines (magnet offers exist, expensive!)
Cost reduction measures needed & started , e.g. Großgeräteantrag submitted
(mainly Rf), in house fabrication of quadrupoles, iron pieces for deflection )
MESA Accelerator Layout –optimization:
Gun
MELBA
MAMBO
MEEK-1
MEEK-2
Recirculation arcs 1-3-5
Recirculation arcs 2-4
Ext. beamline
ERL loop
155 MeV dump
5 MeV dump
P2
MAGIX

## Slide 35: Summary
Construction of the extended MESA hall will delay the construction of the accelerator to at least 2020
But many accelerator parts have been ordered or even built already
We will test the injector up to 2.5 MeV in a test setup in Hall 3 (old part of the buiding). Construction started mid 2016 tests beamtimes can be run till civil construction starts
Cryomodule tests will be performed at HIM in 2017
Parts of experimental setups, detectors etc. can be tested at MAMI
4 PhD students funded by the new Research Training Group GRK 2128 “AccelencE” will contribute to the project from April 2016 on

## Slide 36
Building effects on MESA Accelerator Layout
The new layout provides clear advantages:
  The existing beam dump can be more effectively used for P2 experiment
  In addition, it allows a new experiment: BDX (search for dark matter particles)
  One hall (No. 4) for present stays clear, allowing extensions (additional experiments or instrumentation) in future
Disadvantages of the new layout:
  No accelerator setup till civil construction of the new building is finished
  Already existing start-to-end beam dynamics calculations need to be redone
  Nevertheless the new layout can strongly rely on the old one. Important parts like vertical spreaders and low energy beam transport will stay very close to the old layout.

## Slide 37
Building effects on MESA Accelerator Layout
The new layout provides clear advantages:
  The existing beam dump can be more effectively used for P2 experiment
  In addition, it allows a new experiment: BDX (search for dark matter particles)
  One hall (No. 4) for present stays clear, allowing extensions (additional experiments or instrumentation) in future
Disadvantages of the new layout:
  No accelerator setup till civil construction of the new building is finished
  Already existing start-to-end beam dynamics calculations need to be redone
  Nevertheless the new layout can strongly rely on the old one. Important parts like vertical spreaders and low energy beam transport will stay very close to the old layout.

## Slide 38: MESA/MEEK Cryogenic system
Blue: Cryogenic system envelope
4K System: Provided by PRISMA/KPH (D.Simon/E. Schilling, + 3technicians)
4K/2K by RI/DESY
Interfacing responsible: D. Simon
10 m
Cryoplant MESA
Cryomodule
Cryomodule
Valve box RI / DESY
P2 experiment 15 K GHe
Cryoplant P2

## Slide 39: Simplified P&ID for MESA
LHe pipeline 4.4 K
GHe pipeline 4.4 K
GHe pipeline 16 mbar
GHe pipeline 1.2 bar 300 K
GHe pipeline 10 bar 300 K
LN2 pipeline
GN2 pipeline
5000 l dewar
L280
Sub atmospheric compressor
Subcooler / valve box RI
Valve box HIM
To HIM
To Module 2
Module 1
heater